## Sheet1
				Week 1					Week 2					Week 3					Week 4					Week5
Tasks	People Assigned	Duration		1st jan	2nd jan	3rd jan	4th jan	5th jan	6th jan	7th jan	8th jan	9th jan	10th jan	11th jan	12th jan	13th jan	14th jan	15th jan	16th jan	17th jan	18th jan	19th jan	20th jan	21st jan	22nd jan	23rd jan	24th jan	25th jan	26th jan	27th jan	28th jan	29th jan	30th jan	31st jan	1st Feb	2nd feb	3rd feb	4th feb
			Days	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35
Template
Design website template	Billy Bob	4 days
Home Page
Design Home Page	Billy Bob	2 days
Create Home Page	Billy	3 days
About Us
Design About Us Page	Bobby	2 days
Create About Us Page	Billy	3 days
Products Page
Design Products Page	Billy Bob	4 days
Create Products Page	Billy	4 days
Contacts Page
Design Contacts Page	Billy Bob	2 days
Create Contacts Page	Billy	1 day
Grand Finally
Product Testing	Billy & Bob	5 days
Product Release	Me	1 day
Floating Tasks
Compile Product Info	Me	4 days
Create Website Imagery	Bobby	3 days
Create site Navigation	Bob	1 day
Create About Us Content	Me	2 days
Design Products Page Features	Bobby	1 day
Design Checkout Features	Bobby	1 day
Create Checkout Features	Bob	1 day
Compile contact info	Me	1 day